# Club action log

Keep each agreed job with its owner, due date and result. Country-neutral fields.

Free template from SportsHQ (www.sportshq.app). Adapt freely; check your own constitution and governing body rules where flagged.

This is a manual record. It does not send reminders or update itself. Use it beside the meeting minutes. Keep one current copy where the right club officers can find it.

Club / log owner: ____________________________________________

Last reviewed / next review: ____________________________________________

Date format used in this log: ____________________________________________

# Status words

Open: agreed, but not started.

Doing: the owner has started the work.

Blocked: the owner needs a decision, information or help.

Done: the work has been checked and the result recorded.

Closed without doing: the committee agreed to stop. Keep the reason.

# Blank action record

Copy this block for each new action. Do not erase an old due date when it changes. Add the new date and why it changed.

Action ID / meeting and item reference: ____________________________________________

Action: what will be done: ____________________________________________

Owner / original due date: ____________________________________________

Status / last update: ____________________________________________

New due date / reason for change, if any: ____________________________________________

Result or evidence reference / checked by / date: ____________________________________________

Keep private case details out of this shared log. Link to a restricted record only if the people using the log should know that reference.

# Filled example: done and blocked

Fictional records only. An agreed action is not always a completed action. Dates use year-month-day: 2026-10-03 means 3 October 2026.

| Action / meeting item | Owner / due | Status and next step |
| --- | --- | --- |
| A01 / M01-04: check the booking link and draft a notice | Jo / 2026-10-03 | Done. Link checked and draft saved as notice-v1. Jo finished on 2026-10-03. |
| A02 / M01-04: review the booking notice | Lee / 2026-10-04 | Done. Lee checked notice-v1 on 2026-10-04. Posting is a separate action. |
| A03 / M02-02: post the approved notice | Pat / 2026-10-07 | Blocked: key needed. Chair to help. New due date 2026-10-10 agreed at M02. |

# At the next meeting

Start with open, doing and blocked actions.

Ask the owner what has changed. Record facts, not just 'in progress'.

Agree help or a new date where needed. Keep the reason.

Mark work done only after the result has been checked.

Keep completed entries so the next committee can see what happened.

# Before you share it

[  ] Every action has one owner and a clear next step.

[  ] Due dates are clear to everyone reading the file.

[  ] Private details are in the right restricted record.

[  ] Changes have a date and a reason.

[  ] The committee knows where the current copy is kept.